## Usecases
USE CASES		Itrackerhibernate (3.0)					Itrackernodto (3.1)
Label	Description	24.11.05	01.12.05	08.12.05	15.12.05	22.12.05	29.12.05	24.11.05	01.12.05	08.12.05	15.12.05	22.12.05
Total failed:		7	0	0	0	0	0	0	0	0	0	0
Total passed:		127	0	0	0	0	0	0	0	0	0	0
Total tested:		134	0	0	0	0	0	0	0	0	0	0
Project Administration
pro_list	list projects	Passed
proj_list_active	signal active	Passed
proj_list_view	signal vieweable only	Passed
proj_list_locked	signal locked	Passed
proj_create	create new project	Passed
proj_create_owner	add owner on create	Passed
proj_update	update project	Passed
proj_update_name	change name	Passed
proj_update_desc	change description	Passed
proj_update_view	change to status vieweable only	Passed
proj_update_locked	change to status locked	Passed
proj_update_active	change to status active	Passed
proj_add_owner	add owner on update	Passed
proj_remove_owner	remove owner on update	Passed
proj_chg_options	change seven options	Passed
proj_create_workflow	create new workflow script	Failed
proj_create_version	create new version	Passed
proj_create_component	create new component	Passed
proj_view_attachment	view all attachements	Passed
vers_update_name	Change name of a version entity	Passed
vers_update_desc	Change description of a version entity	Passed
comp_update_name	Change the name of a component	Passed
comp_update_desc	Change the description of a component	Passed
		23 (1/22)	0 (0/0)	0 (0/0)	0 (0/0)	0 (0/0)	0 (0/0)	0 (0/0)	0 (0/0)	0 (0/0)	0 (0/0)	0 (0/0)
User Administration
user_list	list users	Passed
user_list_locked	signal locked user	Passed
user_list_online	Show online status of a user	Passed
user_create	create user	Passed
user_create_eq_pwd	Check pwd is equal to pwd confirmation on create	Passed
user_create_perm_first	grant 13 user permissions to first project on create	Passed
user_create_perm_any	grant 13 user perm. to a project not first/last on create	Passed
user_create_perm_last	grant 13 user permissions to last project on create	Passed
user_create_su	grant super user rights on create	Passed
user_create_no_su	Do not grant super user rights on create	Passed
user_create_check_email	Check email format on create	Passed
user_update	update user	Passed
user_update_eq_pwd	Check pwd is equal to pwd confirmation on update	Passed
user_update_fname	Change firstname of a user	Passed
user_update_lname	Change lastname of a user	Passed
user_update_fname	Change firstname of a user	Passed
user_update_login	Change loginname of a user	Passed
user_update_email	Change email address of a user	Passed
user_update_check_email	Check email format on update	Passed
user_update_pwd	Change passwort of a user	Passed
user_grant_su	Grant super user rights to a user	Passed
user_ugrant_su	Ungrant super user rights to a user	Passed
user_grant_perm_first	grant 13 user permissions to first project	Passed
user_grant_perm_any	grant 13 user permissions to a project not first/last	Passed
user_grant_perm_last	grant 13 user permissions to last project	Passed
user_ugrant_perm_first	ungrant 13 user permissions to first project	Passed
user_ugrant_perm_any	ungrant 13 user permissions to a project not first/last	Passed
user_ugrant_perm_last	ungrant 13 user permissions to last project	Passed
user_lock	lock user	Passed
		29 (0/29)	0 (0/0)	0 (0/0)	0 (0/0)	0 (0/0)	0 (0/0)	0 (0/0)	0 (0/0)	0 (0/0)	0 (0/0)	0 (0/0)
Configuration administration
status_overview	Show overview page	Passed
status_add	Add a new status	Passed
status_update_value	Update the status value	Passed
status_update_order	Update the status order	Failed
status_update_lang	Updateall language strings	Passed
status_remove	Remove a status	Passed
severities_add	Add a severity	Passed
severities_update_lang	Update a severities languages strings	Passed
severities_move_up	Move a severity up in the soring order	Passed
severities_move_down	Move a severity down in the soring order	Passed
severities_remove	Remove a severity	Passed
resolution_add	Add a resolution	Passed
resolution_update_lang	Update a resolutions languages strings	Passed
resolution_move_up	Moves a resolution up in the sorting order	Passed
resolution_move_down	Moves a resolution down in the sorting order	Passed
resolution_remove	Remove a reolution	Passed
custfield_add	Add a custome field	Passed
custfield_update_lang	Update a custom fields language strings	Passed
custfield_update_type	Update a custom fields type	Passed
custfield_update_required	Update a custom fields required flag	Passed
custfield_update_sort	Update a custom fields sort options flag	Passed
custfield_update_datef	Update a custom fields date format	Passed
custfield_add_option	Add an option to a custom list	Passed
custfield_update_opt_lang	Update the language strings of a option	Passed
custfield_remove_option	Remove an option from a custom list	Passed
custfield_remove	Remove a custom field
data_export	Export data as xml	Passed
data_import	Import data from xml file
		26 (1/25)	0 (0/0)	0 (0/0)	0 (0/0)	0 (0/0)	0 (0/0)	0 (0/0)	0 (0/0)	0 (0/0)	0 (0/0)	0 (0/0)
Workflow Administration
wrkfl_create	Create a new workflow script	Passed
wrkfl_create_syntax	Validate syntax of script on create	Passed
wrkfl_update_name	Update the scripts name	Passed
wrkfl_update_event	Update the event on which the script will be triggered	Passed
wrkfl_update_syntax	Validate syntax of script on create	Passed
wrkfl_remove	Remove a workflow script	Passed
		6 (0/6)	0 (0/0)	0 (0/0)	0 (0/0)	0 (0/0)	0 (0/0)	0 (0/0)	0 (0/0)	0 (0/0)	0 (0/0)	0 (0/0)
Language Administration
lang_list	list languages	Passed
lang_update	Update all language strings	Passed
lang_update_base	Update all language strings of the base language	Passed
lang_reinitialize	Reinitialize all resource strings
lang_create_ctry	Create a new country language for a given locale	Passed
lang_export	Export a language to a property file	Passed
lang_create_lang	Create a new language	Passed
lang_create_key	Create a new key	Passed
		7 (0/7)	0 (0/0)	0 (0/0)	0 (0/0)	0 (0/0)	0 (0/0)	0 (0/0)	0 (0/0)	0 (0/0)	0 (0/0)	0 (0/0)
Attachment Administration
attch_list	List attachements	Passed
attch_upload_db	Create db entry on upload	Passed
attch_upload_file	Save file on upload	Passed
attch_delete_db	Delete db record on delete	Passed
attch_delete_file	Delete file data on delete	Passed
		5 (0/5)	0 (0/0)	0 (0/0)	0 (0/0)	0 (0/0)	0 (0/0)	0 (0/0)	0 (0/0)	0 (0/0)	0 (0/0)	0 (0/0)
Scheduler Administration
task_list	List tasks	Passed
task_create	Create a new Task	Passed
task_update	Update a task	Passed
task_update_months	Update the months attribute	Passed
task_update_days	Update the days attribute	Passed
task_update_hours	Update the hours attribute	Passed
task_update_minutes	Update the minutes attribute	Passed
task_update_weekday	Update the weekdays attribute	Passed
task_update_predefined	Change predefined task	Passed
task_update_classname	Update the classname attribute	Passed
task_update_classcheck	Check availability of chosen class	Passed
task_delete	Delete a task	Passed
		12 (0/12)	0 (0/0)	0 (0/0)	0 (0/0)	0 (0/0)	0 (0/0)	0 (0/0)	0 (0/0)	0 (0/0)	0 (0/0)	0 (0/0)
My Preferences
prefs_show	Show form	Passed
prefs_change_fname	Change first name	Passed
prefs_change_lname	Change last name	Passed
prefs_change_email	Change the email address	Passed
prefs_change_pwd	Change the password	Passed
prefs_change_checkpwd	Check the previous password	Passed
prefs_change_pwdeq	Check equality of password and confirmation	Passed
prefs_change_lang	Change the language	Passed
prefs_change_save	Change save login	Failed
prefs_change_indnum	Change number of issue on index	Passed
prefs_change_prjnum	Change numbers of issue on project	Passed
prefs_change_showclosed	Change show closed issues	Failed
prefs_change_sortorder	Change sort order field of issue ordering	Passed
prefs_change_search	Change remember last search	Failed
Prefs_change_tags	Change 'Use text tags'	Failed
prefs_hide_assigned	Hide assigned issues	Passed
prefs_hide_unassigned	Hide unassigned issues	Passed
prefs_hide_created	Hide created issues	Passed
prefs_hide_watched	Hide watched issues	Passed
prefs_show_assigned	Show assigned issues	Passed
prefs_show_unassigned	Show unassigned issues	Passed
prefs_show_created	Show created issues	Passed
prefs_show_watched	Show watched issues	Passed
		23 (4/19)	0 (0/0)	0 (0/0)	0 (0/0)	0 (0/0)	0 (0/0)	0 (0/0)	0 (0/0)	0 (0/0)	0 (0/0)	0 (0/0)
Issue Search

search_text	Search for a text string	Failed
		1 (1/0)	0 (0/0)	0 (0/0)	0 (0/0)	0 (0/0)	0 (0/0)	0 (0/0)	0 (0/0)	0 (0/0)	0 (0/0)	0 (0/0)
Preferences Administration

pref_update_pass	change password
		0 (0/0)	0 (0/0)	0 (0/0)	0 (0/0)	0 (0/0)	0 (0/0)	0 (0/0)	0 (0/0)	0 (0/0)	0 (0/0)	0 (0/0)
Issue Quick Search

search_issue	Search for an issue number through quick view	Passed
	Search an issue that does not exist	Passed
		2 (0/2)	0 (0/0)	0 (0/0)	0 (0/0)	0 (0/0)	0 (0/0)	0 (0/0)	0 (0/0)	0 (0/0)	0 (0/0)	0 (0/0)

## Checklist
Project Test Check List

Compiles without errors
Will run and create a Login Page in browser
Will not grow database with each (re)start.
	Can log on
		home page displays correctly
		Check changes
	Open Admin page
		list/add project
		list/add user
		check changes
	Open Project List page
		List projects
		List issues
		Create new issue and associated information
		Edit existing issue and associated information
		View issue and associated information
		Check changes
	Open Issue Search
		run search
		check changes
	Open Issue Reports
		List reports
		Run reports
		Check changes
	Open Project Admin
		List projects
		Edit project
		Check changes
	Open My Preferences
		Change preferences
		Check changes
Checkin version

## Statistics
Itrackerhibernate
	Failed	Passed	Total	Miss-Ratio	Ratio-Delta
24.11.05	7	127	134	0.05
01.12.05	0	0	0	0	-0.05
08.12.05	0	0	0	0	0
15.12.05	0	0	0	0	0
22.12.05	0	0	0	0	0
29.12.05	0	0	0	0	0